## Sheet1
Task No. | Date | Tasks Completed
1 | 2014-07-25 | Contract DAO Implementation AttendanceLog DAO Implementation
2 | 2014-07-26 | GUI Planning and Design Electric Reading DAO Implementation Bill DAO Implementation Water Reading DAO Implementation
3 | 2014-07-29 | Exceptions Class Error Handling
4 | 2014-07-31 | Tenant Module: Working Display Tenant Report Module: View tenant's contract
5 | 2014-08-02 | Tenant Module: Working Add Tenant w/ existing guardian
6 | 2014-08-03 | User Stories Finalization
7 | 2014-08-04 | Using Blob data type for storing images in database
8 | 2014-08-07 | Room Module: View Room Assignment
9 | 2014-08-08 | Room Module: Assign Tenant to Room
10 | 2014-08-09 | Bill Module: Add Bill
11 | 2014-08-10 | Log Module: Add Log, View Log, LogIn/Out
12 | 2014-08-11 | User Stories Update
13 | 2014-08-12 | Test Cases Optimization Tenant Module: Working Edit Tenant
14 | 2014-08-13 | Bill Module: Change Bill Status
15 | 2014-08-16 | Bill Module: Edit Bill
16 | 2014-08-17 | Report Module: View Leaving Tenants by Contract and year of Graduation
17 | 2014-08-19 | GUI Implemenatation, GUI Creatives
18 | 2014-08-20 | Report Module: Renew Contract
19 | 2014-08-25 | Final Revisions and Testing