## Iteration 1
Iteration 1
Role | Tasks | Estimated Hours | Date Completed | Contributors
Analyst | Problem Analysis | 6 hours | 2014-07-10 | Ann, Janae, Jao, Paul
| User Stories | 8 hours | 2014-07-19 | Ann, Janae, Jao, Paul, Jude
| Identification of the Problem | 4 hours | 2014-06-21 | Ann, Janae, Jao, Paul
| Business Process | 2 hours | 2104-06-20 | Janae
| Interview | 2.5 hours | 2014-06-17 | Ann, Jao
| Initial GUI | 8 hours | 2014-07-11 | Paul - View, Add, Delete, Add Tenant ; Jao - Add, View Edit Room, Ann - Main Menu, Edit Page, Tenant Page
Developer | EER Diagram | 6 hours | 2014-07-02 | Giodee, Jude, Danica
| SQL Database | 2 hours | 2014-07-02 | Jude
| Class Diagram | 8 hours | 2014-07-05 | Giodee, Jude, Danica
| Beans | 1 hour | 2014-07-05 | Giodee
| DAO | 1 hour | 2014-07-05 | Giodee, Adrian
| Tenant DAO Implementation | 4 hours | 2014-07-07 | Giodee, Danica, Adrian
| Guardian DAO Implementation | 2 hours | 2014-07-07 | Giodee, Danica, Adrian
| Room DAO Implementation | 3 hours | 2014-07-07 | Giodee, Danica, Adrian
| Error Handling | 2 hours | 2014-07-08 | Adrian
| Connecting to GUI | 1 hour | 2014-07-09 | Giodee, Adrian
| Attendance DAO Implementation | 3 hours | 2014-07-10 | Danica
| Bill DAO Implementation | 4 hours | 2014-07-13 | Giodee, Danica
| Contract DAO Implementation | 4 hours | 2014-07-13 | Giodee
Quality Assurance | Test Cases | 10 hours | 2014-07-17 | Kevin, Rolf
| Class Diagram Checking | 8.5 hours | 2014-07-04 | Angelo, Kevin, Jude
| User Stories Checking | 2.5 hours | 2014-07-15 | Angelo, Kevin, Jude
| Software Testing and Debugging | 10 hours | every software update | Kevin, Rolf, Jude

## Iteration 2
Iteration 2
Role | Tasks | Estimated Hours | Date Completed | Contributors
Analyst | GUI Planning and Design | 6 hours | 2014-07-26 | Ann, Janae, Jao, Paul, Jude
| GUI Implementation | 15 hours | 2014-08-19 | Jao
| GUI Creatives | 18 hours | 2014-08-19 | Ann and Paul
| User Stories Update | 2 hours | 2014-08-11 | Jao, Jude
Developer | Exceptions Class Error Handling | 2 hours | 2014-07-29 | Adrian, Giodee, Danica
| Contract DAO Implementation | 2 hours | 2014-07-25 | Giodee
| Electric Reading DAO Implementation | 1 hour | 2014-07-26 | Giodee, Danica
| Bill DAO Implementation | 2 hours | 2014-07-26 | Giodee
| Tenant Module: Working Edit Tenant | 2 hours | 2014-08-12 | Adrian
| Tenant Module: Working Add Tenant w/ existing guardian | 3 hours | 2014-08-02 | Adrian
| Tenant Module: Working Display Tenant | 2 hours | 2014-07-31 | Danica
| Water Reading DAO Implementation | 1 hour | 2014-07-26 | Danica
| AttendanceLog DAO Implementation | 1 hour | 2014-07-25 | Giodee, Danica
| Using Blob data type for storing images in database | 1 hour | 2014-08-04 | Adrian
| Room Module: Assign Tenant to Room | 2 hours | 2014-08-08 | Danica, Adrian
| Room Module: View Room Assignment | 3 hours | 2014-08-07 | Danica, Adrian
| Bill Module: Add Bill | 1 hour | 2014-08-09 | Giodee
| Bill Module: Edit Bill | 3 hours | 2014-08-16 | Danica
| Bill Module: Change Bill Status | 1 hour | 2014-08-13 | Danica
| Log Module: Add Log | 6 hours | 2014-08-10 | Giodee
| Log Module: View Log | 7 hours | 2014-08-10 | Giodee
| Log Module: Log in and out | 2 hours | 2014-08-10 | Giodee, Danica
| Report Module: View leaving tenants by contract | 2 hours | 2014-08-17 | Danica, Adrian
| Report Module: View leaving tenants by year of grad | 3 hours | 2014-08-17 | Giodee
| Report Module: View tenant's contract | 4 hours | 2014-07-31 | Giodee
| Report Module: Renew Contract | 5 hours | 2014-08-20 | Giodee
| Final Revisions | 12 hours | in progress | Giodee, Danica, Adrian
Quality Assurance | Test Cases Optimization | 3 hours | 2014-08-12 | Angelo
| User Stories Finalization | 1 hour | 2014-08-03 | Angelo
| Final Testing | 5 hours | in progress | Kevin , Rolf , Angelo, Jude
| Tenant Module Testing: Working Edit Tenant | 1 hour | every software update | Kevin , Rolf , Angelo, Jude
| Tenant Module Testing: Working Add Tenant | 1 hour | every software update | Kevin , Rolf , Angelo, Jude
| Tenant Module Testing: Working Display Tenant | 1 hour | every software update | Kevin , Rolf , Angelo, Jude
| Room Module Testing: Assign Tenant to Room | 1 hour | every software update | Kevin , Rolf , Angelo
| Room Module Testing: View Room Assignment | 1 hour | every software update | Kevin , Rolf , Angelo
| Bill Module Testing: Add Bill | 1 hour | every software update | Kevin ,Rolf , Angelo
| Bill Module Testing: Edit Bill | 1 hour | every software update | Kevin , Rolf , Angelo
| Bill Module Testing: Change Bill Status | 1 hour | every software update | Kevin , Rolf , Angelo
| Log Module Testing: Add Log | 1 hour | every software update | Kevin , Rolf , Angelo
| Log Module Testing: View Log | 1 hour | every software update | Kevin , Rolf , Angelo
| Report Module Testing: View leaving tenants by contract | 1 hour | every software update | Kevin , Rolf , Angelo
| Report Module Testing: View leaving tenants by year of grad | 1 hour | every software update | Kevin , Rolf , Angelo
| Report Module Testing: View tenant's contract | 1 hour | every software update | Kevin , Rolf , Angelo
| Report Module Testing: Renew Contract | 1 hour | every software update | Kevin , Rolf , Angelo